## Executive Summary
Phase 2 Executive Summary
Total roadmap items | 25
Done | 9
Partial | 9
Not Started | 7
Legend | Green = done | Amber = partial | Red = not started
Note | This summary reflects the current codebase status and is meant for quick manager review.

## Phase2 Tracker
Serial | Phase 2 Item | Description | Status | Already Done | Still Pending
1 | Universal Data Connector Framework | Unified connector layer for multiple enterprise data sources, automatic schema discovery, connection validation, and metadata creation. | Done | Database connector service, admin source console, test connection, schema/table discovery, source selection. | Add more connectors later: MySQL, SQL Server, cloud warehouses, APIs, file storage.
2 | Audit Workspaces & Engagement Management | Isolated audit workspaces with separate conversations, datasets, evidence, and reports. | Done | Workspace management, active workspace selection, isolated workspace scoping in the app. | Add richer engagement lifecycle and workspace reporting.
3 | Role-Based Access Control (RBAC) | Role-based authentication and authorization for auditors, managers, reviewers, compliance officers, and admins. | Done | Login, signup, admin role control, access restrictions, protected admin views. | Add finer-grained permissions and policy-based access controls.
4 | Multi-User Collaboration Platform | Shared investigations, comments, mentions, tasks, approvals, and version history. | Partial | Chat sessions and workspace separation exist. | Shared comments, mentions, task assignment, collaborative review, version history.
5 | Continuous Audit Monitoring | Scheduled monitoring of transactions, approvals, vendor records, and compliance data. | Partial | Live updates and websocket-based real-time UI support exist. | Scheduled monitors, alert rules, automated investigations from events.
6 | AI Audit Agent Marketplace | Plug-and-play audit agents for payroll, procurement, vendor risk, ITGC, SOX, tax, cybersecurity, HR, etc. | Not Started | Core audit agents exist. | Marketplace UI, agent registry, activation rules, packaging.
7 | Investigation Knowledge Graph | Graph visualization linking employees, vendors, invoices, approvals, contracts, departments, bank accounts, and transactions. | Not Started | Entity-centric investigations exist. | Graph model, relationship extraction, visual investigation pathing.
8 | Enterprise Knowledge Graph | Central organizational graph for semantic retrieval, reasoning, and recommendation context. | Not Started | Document and entity metadata exist. | Persistent enterprise graph store and update pipeline.
9 | Advanced Semantic Search | Unified search across structured data, PDFs, policies, contracts, emails, spreadsheets, presentations, and chat history. | Partial | Hybrid retrieval, semantic document search, evidence extraction. | One search layer across all repositories and full corpus coverage.
10 | AI-Powered Control Testing | AI-driven internal control tests for approvals, segregation of duties, policy exceptions, duplicates, and failed controls. | Not Started | Risk and findings exist. | Control library, rule execution, evidence-backed test results.
11 | Compliance Intelligence Engine | Natural-language compliance layer for SOX, COSO, ISO 27001, COBIT, GDPR, HIPAA, PCI-DSS, and internal policies. | Partial | Compliance-oriented investigation patterns and compliance-aware agent logic. | Regulation mapping, policy clause retrieval, rule interpretations.
12 | AI-Based Risk Assessment Engine | Dynamic AI-driven risk scoring across financial, compliance, historical, and behavioral dimensions. | Done | Evidence-aware risk scoring service and calibrated risk levels. | Optional future ML calibration and predictive signals.
13 | Intelligent Finding & Recommendation Engine | Evidence-backed findings with root cause, impact, and actionable recommendations. | Done | Finding generation, recommendation generation, audit-style narratives. | Add richer root-cause decomposition and policy context.
14 | Automated Workpaper Generation | Record query, evidence, SQL, citations, reasoning path, and validation into standardized workpapers. | Partial | Traceability, execution metadata, evaluation, evidence records. | Formal workpaper templates and export packaging.
15 | AI Audit Report Generation | Full audit reports with objectives, scope, methodology, observations, evidence, risk, and recommendations. | Partial | Audit-style response composition exists. | Report templates, export to PDF/Word/Excel/PPT.
16 | Audit Workflow Automation | Investigation, review, approval, management response, remediation, validation, closure. | Partial | Planner/orchestrator and multi-step audit flows exist. | Stage transitions, approvals, closure tracking.
17 | Enterprise Dashboards & Executive Analytics | Interactive dashboards for progress, risk distribution, findings, remediation, and compliance trends. | Done | Dashboard pages, charts, KPI cards, investigation summaries. | More stakeholder-specific dashboards.
18 | AI Conversation Memory & Organizational Context | Persistent memory for prior investigations, recurring findings, historical reports, and user interactions. | Done | Conversation sessions, follow-up context, memory, active investigation state. | Long-term organizational memory and historical pattern recall.
19 | Smart Notifications & Alerting System | Email, Teams, Slack, and webhook notifications for high-risk events and overdue actions. | Not Started | Real-time app updates exist. | Outbound notifications and alert delivery channels.
20 | Explainable AI & Decision Transparency | Complete visibility into reasoning, evidence, SQL, citations, confidence, validation, and agent flow. | Done | Traceability tab, execution metadata, Langfuse integration, evaluation output. | Better visual trace summaries and downloadable audit trails.
21 | Enterprise AI Copilot Across the Platform | Context-aware copilots embedded in pages, profiles, evidence viewers, dashboards, and investigations. | Partial | Copilot chat, contextual uploads, page-linked responses. | Per-page inline copilot actions and richer contextual prompts.
22 | Predictive Risk & Fraud Analytics | ML models predicting future risk, fraud, vendor anomalies, and control failures. | Not Started | Rule-based and evidence-aware risk scoring exist. | Forecasting models and predictive signals.
23 | Data Governance & Audit Trail Management | Comprehensive audit trail for user actions, AI responses, data access, evidence changes, and approvals. | Done | Governance audit logging, traceability, router reviews, action logs. | Enhanced admin reporting and retention policies.
24 | Performance, Scalability & Distributed Processing | Async task execution, distributed orchestration, background scheduling, caching, load balancing, and horizontal scaling. | Not Started | Current system is functional for demo scale. | Distributed processing, queueing, cache, scale controls.
25 | Enterprise Integration & API Ecosystem | Integrations with ERP, ticketing, governance, SIEM, identity, document management, and BI platforms. | Partial | Generic database connector layer and internal APIs exist. | External ERP/ticketing/SIEM/BI integrations.

## Daywise Plan
Day | Focus | Related Phase 2 Item | Implementation Goal | Status
1 | Collaborative workspace enhancements | 4 | Add shared comments, mentions, tasks, and review flow inside workspaces. | Done
2 | Continuous monitoring + alerts | 5 + 19 | Add scheduled monitoring jobs, event triggers, and notification delivery. | Done
3 | Semantic search expansion | 9 | Broaden retrieval coverage across documents, emails, spreadsheets, and chat memory. | Done
4 | Compliance intelligence | 11 | Map regulations/policies to findings and improve compliance-focused reasoning. | Done
5 | Control testing engine | 10 | Automate control tests for approvals, exceptions, SoD, and duplicates. | Done
6 | Workpapers + report generation | 14 + 15 | Convert traceability and findings into formal audit workpapers and report exports. | Done
7 | Workflow automation | 16 | Add explicit investigation/review/approval/remediation/closure stages. | Done
8 | Knowledge graph foundation | 7 + 8 | Model entity relationships and prepare graph-based investigation views. | Not Started
9 | Predictive risk analytics | 22 | Add forecast signals and anomaly prediction on top of scoring and history. | Not Started
10 | Marketplace + enterprise integrations | 6 + 25 | Prepare plugin/agent catalog and external system connectors. | Partial